## Slide 1: Agentic Workflow Teaching Pilot
Week 3 - 2026-05-08 - owner: Training Enablement Team

## Slide 2: Executive summary
The pilot converted four representative workflows into small runnable teaching demos. The current focus is validation, reviewer checkpoints, and safe execution boundaries.
Demos included: 4
Validation is scripted; final messaging requires human review.

## Slide 3: Progress by workstream
Demo 0 report workflow: done (100%), risk=low
Demo 1 spec portability: done (95%), risk=medium
Demo 2 rich document pipeline: in review (85%), risk=medium
Demo 3 permission guardrails: done (90%), risk=medium

## Slide 4: Risks and blockers
Need instructor review of the exact classroom timing.
Need sanitized real examples before company-specific rollout.
Confirm whether workshop should use Cline, OpenCode, or both for live demo.
Decide which demo will be the hands-on exercise.

## Slide 5: Human review checklist
Does the report reflect only the provided status data?
Are risks stated without overstating certainty?
Are decision requests explicit?